## Estimation Effort
Cintana Technologies
Name | G.Mythreyi
ID | T0005
Tasks Assigned from 24/04/2017 to 27/042017 | Time Estimation | Effort | Status
Project Details Screen which includes all the operations like select edit delete of all the donor screens | 16 hrs | 24hrs(3 days) | completed
Asynchronous Execution using nodejs | 8 hrs | 10 hrs | completed
Tasks Assigned for 2/3/2018 - 5/5/2018 | Time Estimation | Effort | Status
Enhancements in Project Detail Screen | 7 hrs | 8hrs | Completed
New Screen For attaching Invitation or newsletters | 1Day | 2hrs from started | need to complete
Tasks Assigned for 7/5/2018 | Time Estimation | Effort | Status
New Screen For attaching Invitation or newsletters | 1 day | 1 day | completed
local passport authentication | 8hrs | 10 hrs | completed
facebook passport authentication |  |  | need to complete
google passport authentication |  |  | completed
Tasks Assigned for 8/5/2018 | Time Estimation | Effort | Status
facebook passport authentication | 5hrs | 6hrs | need to complete
Ionic Framework learning basics | 3 hrs | 6 hrs
Tasks Assigned for 9/5/2018 | Time Estimation | Effort | Status
Login Page and tabs page | 3 hrs | 4 hrs | completed
Nicholas meeting | 3 hrs
questions and doubts discussion | 40 mins
Tasks Assigned for 10/5/2018 | Time Estimation | Effort | Status
Login page with all the UI components |  |  | completed
Creating types of questionaries fileds |  |  | completed
Nicholas Component discussion |  |  | completed
AIM for Seva Client demo |  |  | completed
Tasks Assigned for 11/5/2018 | Time Estimation | Effort | Status
Creating summary page and passing data to that page
form validation
date picker
Aim for Seva fixes(attachment)
Tasks Assigned for 12/5/2018 | Time Estimation | Effort | Status
Aim for Seva fixes(attachment) |  | 7 hrs | not completed
passing data between two pages(ionic)